## Knowledge Transition
KT List of Tasks /Activities |  | Status | KT <Provider> | KT <Receivers> | # of Hours Required | Start Date | End Date | Comments
CloudBees Operation Center (Infrasture) |  | Completed | Mohammed | Karthik Kasker, Neelima, Krishnan, Siva | 2 hours
Jnekins master-1,2 nodes (Infrastructure) |  | Completed | Mohammed | Karthik Kasker, Neelima, Krishnan, Siva
GitHub (Infrastrucure) |  | Completed | Mohammed | Karthik Kasker, Neelima, Krishnan, Siva
CloudBees Operation Center (Installation) |  | In-Progress | Mohammed | Karthik Kasker, Neelima, Krishnan, Siva | 1 | 2021-11-19
Jenkins Master (Installation) |  | In-Progress | Mohammed | Karthik Kasker, Neelima, Krishnan, Siva
GitHub (Installation) |  | In-Progress | Mohammed | Karthik Kasker, Neelima, Krishnan, Siva
AWS |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh
IAM |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh
KMS |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh
IAM Serivce Account Users |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh
IAM Policy |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh
IAM Roles (OKTA/DUO) |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh
SQS |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh
SES |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh
S3 |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh,Mahalakshmi
Security Group
VPC/Subnet/Routetable/Intergateway/
Secret Manager (Suresh) |  |  | Suresh
siva
SNS |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh,Mahalakshmi
IDP (Identity Provider)
Route-53
Cloudflare
Certification Manager
Active Directory Inegration
Network ACL |  |  | Suresh | Venkatesh, Siva, Maizull, Sekhar ,Rakesh,Mahalakshmi, Jattin, Akash, Dhruv
CloudFormation (BaseLine Infrastructure Implementation |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh,Mahalakshmi
Ec2 Server /CFT |  | Completed | Mohammed | Venkatesh, Siva, Maizull, Sekhar ,Rakesh,Mahalakshmi
CloudWatch / CloudTrail/Config |  |  |  | Venkatesh, Siva, Maizull, Sekhar ,Rakesh,Mahalakshmi
(Insert rows as needed)
| TOTAL Effort Required |  |  |  | 1 | Dates & Totals in this box are auto-generated
| Start/End Dates for KT |  |  |  |  | 2021-11-19 | 0
|  | Name |  |  |  | Date
Component Sign-Off | Person Giving KT
Person Receiving KT
* Refer to the Component Instructions page to complete Part v.
Note on C2: Current status of this task - Not Started, In Progress, Complete
Note on F2: The amount of time KT will take for this task. NOTE: show hours in decimal format, e.g. 15 mins is shown as 0.25 1 hour and 30 mins is shown as 1.5
Note on G2: The planned start date for this task DD/MM/YYYY
Note on H2: The planned end date for this task DD/MM/YYYY
Note on F39: Please confirm that this cell is a sum of the hours listed in the cells above
Note on G40: Confirm that this is the earliest start date for any task above
Note on H40: Confirm that this is the latest End date for any task above